## EXAMPLE - Scrum Standup Mtg
WEEKLY SCRUM MEETING
| PROJECT NAME | Colligo |  |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE | Discord Clone
| PROJECT MEMBERS | Enesh Jakhar, Artem Khachaturov, Roarke De Crewe, Bassim Beshry, Jordan Pohr |  |  | 2024-01-21 | 2024-04-16
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION in days | STATUS | COMMENTS
No | SPRINT 1 (Requirements) |  |  |  | 0 | 0
No | Feature 1 | Discord Server Creation | Entire Group |  | 25/01/2024 |  |  | Complete
No | Feature 2 | Github Creation | Entire Group |  | 25/01/2024 |  |  | Complete
No | Feature 3 | Basic Requirement Definition | Entire Group |  | 25/01/2024 |  |  | Complete
No | Feature 4 | UML Diagram | Entire Group |  | 25/01/2024 |  |  | Complete
No | SPRINT 2 (Milestone 2) |  |  |  | 0 | 0
No | Feature 5 | Product Description | Artem Khachaturov |  | 04/02/2024 |  |  | In Progress | started In week 5.
No | Feature 6 | Requirements analysis and development | Roarke De Crewe, Bassim Beshry, Jordan Pohr |  | 04/02/2024 |  |  | In Progress | started In week 5.
No | Feature 7 | User stories | Enesh Jakhar |  | 04/02/2024 |  |  | In Progress | started In week 5.
No | Feature 8 | Use case diagram and descriptions | Enesh Jakhar, Artem Khachaturov & Roarke De Crewe |  | 04/02/2024 |  |  | In Progress | started In week 5.
No | SPRINT 3 |  |  |  | 0 | 0
No | Feature 8 | [6 empty] | Not Started
No | Feature 9 | [6 empty] | Not Started
No | Feature 10 | [6 empty] | Not Started
Formulas:
START DATE = MIN([START DATE, row below]:G10)

## BLANK - Scrum Standup Mtg
WEEKLY SCRUM STANDUP MEETING TEMPLATE
| PROJECT NAME |  |  |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
| PROJECT MANAGER | [6 empty] | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION in days | STATUS | COMMENTS
| SPRINT 1 |  |  |  | 0 | 0
Feature 1
Feature 2
Feature 3
| SPRINT 2 |  |  |  | 0 | 0
Feature 4
Feature 5
Feature 6
| SPRINT 3 |  |  |  | 0 | 0
Feature 7
Feature 8
Feature 9
Double click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options.

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.